## Taul1
Month | 04/2012 | 05/2012 | 06/2012 | 07/2012 | 08/2012 | 09/2012 | 10/2012 | 11/2012 | 12/2012 | 01/2013 | 02/2013 | 03/2013 | 4/2013 | 5/2013 | 6/2013 | 7/2013 | 8/2013 | 9/2013 | 10/2013 | 11/2013 | 12/2013 | 01/2014 | 02/2014 | 03/2014 | 4 / 2014 | 5 / 2014 | 6 / 2014 | 7 / 2014 | 8 / 2014 | 9 / 2014 | 10 / 2014 | 11 / 2014 | 12 / 2014
Activity
Meetings | Kick off | [5 empty] | Murmansk 4) | Luleå,Apatity 5) |  |  |  |  | Apatity 8) |  | Luleå 10) |  |  | Luleå, Laver 16) | Levi 15) | [11 empty] | Rovaniemi 25)
Conferences | [11 empty] | Oulu 6) | Rovaniemi 9) |  |  |  |  | Apatity 14) |  |  |  |  | Espoo 18) |  | Apatity 19) Austria 20) |  |  |  | China 24)
Project Management
History and background of the case mines and creating updated database of example mine areas | GTK, MI KSC, LTU
Field working and laboratory analyses |  | Apatity 1) | Apatity 2) |  |  | Kemi 3) | [5 empty] | Kemi 7) |  |  |  | Laver 12) |  | Kemi 13) | Kemi 13) | [8 empty] | Laver 21)
[15 empty] | Umbozero 11) | [10 empty] | Kemi 22) Umbozero 23)
Measures and recommendations for improving the conditions
Promoting the network cooperation between different organizations | [19 empty] | Murmansk 17)
1) 28-31.5.2012: Project meeting and visit to Umbozero mine study area. |  |  |  |  | Planning of the field investigations.
2) 18-21.6.2012: Field studies in Umbozero, geophysical measurements, sampling of soil and waters.
3) 27.9.2012: Visit to Kemi Mine; negotiations and visit to field sampling sites; sampling of bottom sediments of waterways in winter 2013.
4) 30.-31.10.2012: Seminar and workshop of Kolarctic ENPI CBC projects, Murmansk.
5) 8-9.11.2012: Reporting of the results and planning of the next year, meetings of the Steering Group and project group / Apatity: Mining. View to the future 20-22nd November.
6) 7.-8.3.2013 Colloquium at Oulu University.
7) 12.3.2013: Sampling of stream sediments in Kemi Mine.
8) 7.-8.4.2013: Geology Day and project meeting in Apatity.
9) 23.-25.4.2013: Conference on Best Environmental Practices in the Mining Sector in the Barents Region.
10) 25-28.6.2013: Conference "Securing the Future - Mining, Metals & the Environment in a sustainable Society", Luleå; and field excursion to Laver Mine. Cancelled.
11) 10.-14.6.2013: Monitoring water quality, sampling and analyzing in Umbozero Mine. GPR-studies, XRF measurements.
12) Field studies in Laver mine.
13) Sampling of waters and stream sediments in Kemi mine. |  |  |  | Analyses.
14) September 2013: Conference "Monitoring of Mining", Apatity. |  |  |  |  | Cancelled.
15) 29-31.10.2013: Conference "FEM - 9th Fennoscandian Exploration and Mining". Meetings of the steering group and project group in Levi, Finland.
16) Project meeting in Luleå University. Visit to Laver mine.
17) End November/Beginning December 2013: Presentations for the public and media, Murmansk. | [7 empty] | Cancelled.
18) 5-6.2.2014: 11th Geochemistry Days, GTK, Espoo. Poster-presentation and Conference publication.
19) 6-7.4.2014: Geology Day, Apatity; meetings of the project group and steering group.
20) 27.4.-2.5.2014: EGU (European Geosciences Union) General Assembly 2014, Vienna, Austria, 27 April-02 May 2014. Presentation of geophysical studies of the project, Conference publication.
21) May-October 2014: Field work, sampling and analyses in Laver.
22) June-August 2014: Field work, sampling and analyses in Kemi.
23) June-August 2014: Field work, sampling and analyses in Umbozero.
24) 18-22.8.2014: 12th IMWA (International Mine Water Association) Congress 2014, Xuzhou, China, August 18-22, 2014. Presentation of the project. | [9 empty] | Congress publications.
25) 28-29.10.2014: Meeting of the steering group and project meeting. Closing seminar of the project, Rovaniemi.